## Overview
PORTFOLIO INTELLIGENCE · BUILD READINESS
v1.0.0 · 8 October 2026 · Design baseline, not a production-ready application
WORK PACKAGES |  | REQUIREMENTS |  | OPEN RELEASE GATES |  | TASKS COMPLETED
66 |  | 99 |  | 16 |  | 0
Wave | Work packages | Completed | Progress | Ready now | NON-NEGOTIABLES
W0 | 8 | 0 | 0% | 1 | Hosted + complete self-hosted
W1 | 10 | 0 | 0% | 0 | Six strategy/research families
W2 | 8 | 0 | 0% | 0 | Six improvement targets incl. recursion
W3 | 7 | 0 | 0% | 0 | Useful free-data / rules-only mode
W4 | 9 | 0 | 0% | 0 | No live broker order submission
W5 | 10 | 0 | 0% | 0 | Human release + user adoption
W6 | 7 | 0 | 0% | 0 | Private learning by default
W7 | 7 | 0 | 0% | 0 | USD100 pilot / USD20 improvement
START WITH T001 · inspect the actual repository and bind real check commands
Update task status only with evidence. Dependency readiness is calculated; it is not permission to spend, connect accounts or deploy.
All waves are part of the same agreed first release. No deadline or low budget silently removes code-level or recursive improvement.
Provider/API permissions, CA/US legal review, real exports, strategy evidence, load, recovery and sandbox behavior remain unverified.
Canonical source: package Markdown + JSON/CSV contracts. This tracker is a working view; reconcile changes back through the task workflow.

## Tasks
IMPLEMENTATION WORK PACKAGES
Editable status/owner fields are working copies. Reconcile changes with canonical planning/backlog.csv; completion requires real evidence.
Task | Wave | Work package | Owner / role | Status | Relative size | Prerequisites | Requirements | Deliverable | Acceptance / evidence | Dependency readiness
T001 | W0 | Repository inspection and check registry | Lead engineer | Not started | M |  | R070,R078,R079,R080,R088,R094 | Record Git root, existing files, instructions, runtime/lockfiles and a reviewed local check registry; do not overwrite existing agent state. | Bootstrap receipt distinguishes observed commands from proposed commands and no application test is fabricated. | Ready
T002 | W0 | Provider rights and deployment matrix | Integration lead | Not started | M | T001 | R011,R018,R021,R048,R053,R057,R073,R094,R095 | Create provider/deployment/use matrices and request required approvals outside the app; gather sanitized export samples. | Every required connector has a permission/auth/field/load plan and unresolved gates stay open. | Waiting
T003 | W0 | Canada and US commercial classification | Qualified counsel + owner | Not started | M | T001 | R007,R021,R055,R079,R094,R095 | Obtain product-specific advice, jurisdiction coverage, privacy/marketing/recordkeeping obligations and launch permissions. | Signed reviewed capability/legal matrix; no disclaimer-only clearance. | Waiting
T004 | W0 | Free-data capability experiment | Data engineer | Not started | M | T001 | R003,R004,R011,R014,R062,R066,R083,R091 | Qualify Alpaca/free historical/EOD inputs and SEC/FX supplementation under actual quotas and rights. | Record observed latency, coverage, misses, normalization and end-to-end free candidate feasibility. | Waiting
T005 | W0 | Named broker and export samples | Integration lead | Not started | M | T002 | R048,R053,R057,R058,R081 | Acquire authorized sample accounts/exports for CIBC, Questrade, IBKR, Wealthsimple and Yahoo; define adapter conformance tests. | Account, holding, cash, transaction, reconnection and round-trip fixtures are provenance-labelled. | Waiting
T006 | W0 | Model API and subscription feasibility | AI engineer | Not started | M | T002 | R018,R023,R025,R027,R074,R085,R095 | Qualify OpenAI/Anthropic/xAI APIs and permitted plan/native routes separately per deployment; verify provider financial-use terms. | No intercepted session credentials; unsupported route remains blocked with exact reason. | Waiting
T007 | W0 | Sandbox and hardware proof | Security engineer | Not started | M | T001 | R033,R036,R037,R038,R076,R086,R092,R096 | Prove bounded gVisor candidate execution on reference Linux and document host/VM compatibility. | Isolation, egress, filesystem, CPU/memory/time limits and no-host-control tests pass or gate stays blocked. | Waiting
T008 | W0 | Architecture and contracts review | Lead + quant + security | Not started | M | T001 | R065,R070,R071,R075,R078,R080,R081,R084,R086,R087,R088,R099 | Review domain boundaries, schemas, financial invariants, proposed tooling and protected control plane. | ADR review and resolved contract assumptions; schema-valid does not mean finance-valid. | Waiting
T009 | W1 | Repository scaffold and quality tools | Platform engineer | Not started | M | T008 | R006,R013,R022,R036,R070,R080,R088,R096,R097 | Create actual Python/React/PostgreSQL workspace, lock approved dependencies and install test/lint/type tools in authorized environment. | Clean bootstrap/build/type/lint receipts and Apache-compatible inventory; core has no UI/provider import dependency. | Waiting
T010 | W1 | Identity and tenant enforcement | Backend + security | Not started | M | T009 | R006,R031,R039,R075,R086,R087 | Implement sessions, membership, least-privilege roles, step-up auth and PostgreSQL tenant enforcement. | Cross-tenant DB/API/job/storage tests and privileged-role separation pass. | Waiting
T011 | W1 | Canonical securities and calendars | Data engineer | Not started | M | T009 | R004,R017,R050,R060,R066,R071,R080,R081,R083,R089,R091 | Implement security/listing/provider identifiers, option identity, corporate-action mapping and versioned exchange calendars. | Ticker collision, rename, DST, half-day, halt and adjusted-contract tests. | Waiting
T012 | W1 | Decimal journal and postings | Backend + quant | Not started | M | T009,T010,T011 | R043,R046,R058,R064,R071,R080,R081,R090,R098 | Implement immutable observations, balanced unit postings, financial journal, reversal/correction and materialized positions. | Ledger idempotency, balance, cash, split, fee and correction property tests plus numeric fixtures. | Waiting
T013 | W1 | Portfolio scopes and source mapping | Backend engineer | Not started | M | T012 | R010,R042,R043,R049,R058,R081,R082 | Implement account/currency/sleeve scopes and explicit mapping of sources to underlying accounts. | Yahoo/broker overlap dedupes once; genuine multiple accounts remain distinct. | Waiting
T014 | W1 | Canonical CSV import preview | Backend + frontend | Not started | M | T013 | R012,R042,R046,R048,R058,R081,R082,R083 | Implement strict parsing, column mapping, dedupe preview, unknown fields, transaction/snapshot distinction and commit revisions. | Malformed/duplicate/mixed-currency/unknown-cost inputs rejected or quarantined with row reasons. | Waiting
T015 | W1 | CIBC and Yahoo CSV adapters | Integration engineer | Not started | M | T005,T014 | R053,R057,R058,R081 | Implement real sample-backed CIBC import and Yahoo list/holdings CSV import/export with loss report. | Actual format round trips verified; watchlists do not create positions and samples remain private. | Waiting
T016 | W1 | Read-only broker connectors | Integration engineer | Not started | L | T002,T005,T010,T013 | R012,R018,R048,R053,R073,R082,R083,R094,R095 | Implement Questrade, IBKR and Wealthsimple sync through approved direct/aggregated routes and secret references. | Per-route approved auth, pagination, token rotation, reconnect, field/freshness and mutation-denial tests. | Waiting
T017 | W1 | Reconciliation and cash availability | Backend + quant | Not started | M | T014,T016 | R012,R043,R049,R058,R071,R080,R081,R082,R083 | Implement observation conflict handling, settled/unsettled/reported cash, open-order commitments and provenance. | Newer user transactions not erased by stale broker snapshots; material conflict blocks sizing. | Waiting
T018 | W1 | Calculation and return engine | Quant engineer | Not started | L | T012,T017 | R043,R046,R064,R068,R071,R080,R081,R082,R090,R098 | Implement valuation, realized/unrealized P&L, TWR, MWR, benchmark flows and FX attribution conventions. | Independent numerical fixtures, multiple-IRR/no-equity/error cases and rounding tolerances. | Waiting
T019 | W2 | MCQ policy builder and consent | Product + backend | Not started | M | T010,T013 | R010,R016,R042,R044,R061,R068,R082 | Implement conditional MCQs/numeric fields, contradiction resolution, policy proposal/review and explicit adoption. | No inferred risk authorization; amount/denominator/currency limits required for affected sizing. | Waiting
T020 | W2 | Policy/risk evaluator | Quant + backend | Not started | M | T017,T018,T019 | R010,R012,R026,R044,R049,R060,R068,R069,R082,R083,R086 | Implement eligibility, cash/concentration/planned-loss/stress constraints and scoped risk pauses/resumption. | Portfolio-feasible alternatives, stop-gap scenarios, deposits/withdrawals and explicit resume tests. | Waiting
T021 | W2 | Data and rights registry | Data + legal liaison | Not started | M | T004,T010,T011 | R003,R011,R014,R021,R066,R073,R083,R091,R094,R095 | Implement explicit provider/feed/rights/entitlement records, revisions, transition policies and no-cross-tenant pooling default. | Unsupported display/model-processing/retention prevents affected use; connected is not qualified. | Waiting
T022 | W2 | Live data and scheduled discovery | Data engineer | Not started | M | T011,T021 | R004,R008,R009,R014,R050,R054,R066,R067,R083,R091 | Implement prioritized streams, EOD/delayed history, coverage accounting, normalized bars and recovery. | 30-symbol planning obeys actual entitlements; missing coverage and retrospective recovery labelled. | Waiting
T023 | W2 | Filings fundamentals and FX ingestion | Data engineer | Not started | M | T021 | R004,R045,R059,R064,R071,R080,R081,R090,R098 | Implement SEC submissions/XBRL publication-aware normalized facts and reference FX ingestion. | Units/restatements/currencies/publication-date and reference-not-executable FX tests. | Waiting
T024 | W2 | Watchlists and monitoring rules | Backend + frontend | Not started | M | T013,T022 | R009,R014,R020,R047,R056,R057,R085,R093 | Implement watchlist CRUD, thesis/conditions/review date, custom deterministic events and priority allocation. | Deletion doesn't alter holdings; dedupe/cooldown/snooze and stale-source tests. | Waiting
T025 | W2 | Durable jobs and outbox | Platform engineer | Not started | M | T009,T010 | R027,R032,R047,R054,R067,R070,R077,R080,R083,R088,R093 | Implement leases, retries/backoff, idempotent consumers, priorities, outbox/inbox and dead-letter handling. | Crash-at-commit and duplicate delivery tests; no exactly-once marketing claim. | Waiting
T026 | W2 | Proposal lifecycle and atomic publication | Backend + quant | Not started | M | T020,T025 | R012,R020,R026,R049,R067,R069,R074,R082,R083,R085,R086 | Implement proposal versions, alternative sets, expiry/invalidation, final revision checks and atomic commitments. | Concurrency test prevents two individually valid proposals overspending; late review cannot activate. | Waiting
T027 | W3 | Strategy registry and qualification states | Quant + backend | Not started | L | T020,T021,T026 | R024,R034,R059,R061,R065,R066,R072,R083,R084,R091,R099 | Implement manifests, bounded configuration, three qualification axes, family policies and user adoption. | Research-only and actionable eligibility are distinct; materially changed strategies need adoption. | Waiting
T028 | W3 | Allocation/rebalance reference | Quant engineer | Not started | M | T027,T018 | R010,R043,R049,R059,R062,R068,R072,R082 | Implement deterministic cash-first underweight allocation with explicit targets, costs and account feasibility. | Free synthetic positive/abstention oracles and conflicting-cash cases pass. | Waiting
T029 | W3 | Quality/value and income references | Quant engineer | Not started | M | T023,T027 | R045,R059,R060,R065,R072,R084,R099 | Implement sector-aware factor policies and distribution sustainability analysis with known missingness. | Negative earnings, incompatible sectors, stale filings and unsustainable headline yield cases handled. | Waiting
T030 | W3 | Swing/momentum reference | Quant engineer | Not started | M | T022,T027 | R008,R009,R059,R060,R062,R065,R072,R084,R099 | Implement 126-session momentum/200-session trend candidate, next-session timing, exit and sizing contract. | No look-ahead, split adjustment mismatch, insufficient history or same-close fill advantage. | Waiting
T031 | W3 | Opening-range breakout reference | Quant engineer | Not started | M | T022,T027 | R008,R009,R050,R059,R065,R066,R067,R072,R083,R084,R091,R099 | Implement 15-minute range candidate, completion buffer, qualified feed and regular-session deadlines. | Partial ranges, provider switches, halts, half-days and expired review block proposals. | Waiting
T032 | W3 | Research datasets and experiment ledger | Research engineer | Not started | M | T023,T027 | R024,R029,R040,R059,R065,R071,R080,R081,R084,R099 | Implement permitted PIT datasets, universe snapshots, full trial ledger and train/development/promotion access separation. | Survivorship, future filings, revision leakage and repeated test access controls demonstrated. | Waiting
T033 | W3 | Backtest and prospective evaluation | Quant researcher | Not started | M | T028,T029,T030,T031,T032 | R024,R029,R040,R059,R062,R065,R084,R099 | Implement chronological cost-sensitive evaluation, dependence-aware statistics, frozen baselines and prospective shadow capture. | Report unsuccessful trials, confidence intervals and limited evidence honestly; no universal edge badge. | Waiting
T034 | W4 | Options identity and risk engine | Options quant | Not started | L | T011,T018,T020 | R017,R043,R044,R068,R082,R089 | Implement explicit deliverables/multipliers, Greeks/model assumptions, collateral and expiry/assignment event states. | Standard and adjusted contract fixtures, spread legging and collateral release tests. | Waiting
T035 | W4 | Options strategy catalogue | Options quant | Not started | M | T021,T027,T034 | R017,R059,R065,R084,R089,R099 | Implement long call/put, covered call, cash-secured put and four directional debit/credit vertical variants. | Whole-package expiry payoffs and pre-expiry scenario risk checked; indicative feed blocks live trade pricing. | Waiting
T036 | W4 | Evidence store and claim graph | AI + data engineer | Not started | M | T010,T023 | R019,R020,R024,R045,R052,R071,R080,R081,R084,R085,R087 | Implement source passages/rights, atomic claim support, citation IDs, revisions, contradiction and retention propagation. | Bad citation, wrong entity/date/unit, syndicated-source duplication and withdrawn evidence cases. | Waiting
T037 | W4 | Model gateway and budget reservations | AI engineer | Not started | M | T006,T010,T025 | R018,R025,R027,R032,R035,R074,R085,R095 | Implement API/native adapters, secrets separation, request bounds, metering and explicit fallbacks. | No authorization/financial-policy/limit bypass; concurrent USD100/USD20 reservations and timeout reconciliation. | Waiting
T038 | W4 | AI researcher and tools | AI engineer | Not started | M | T027,T036,T037 | R015,R024,R045,R059,R074,R084,R085 | Implement independent research thesis generation via allowlisted read tools and structured output. | AI-only thesis path plus unsupported-claim/injection/insufficient-input abstention controls. | Waiting
T039 | W4 | Independent decision evaluator | AI + quant engineer | Not started | M | T026,T036,T037,T038 | R015,R019,R023,R025,R026,R065,R074,R084,R085,R086,R099 | Implement blind-first evidence review, alternatives, bounded revision and final validator handoff. | Separate context receipts, material disagreements block, reviewer-added claims reverified. | Waiting
T040 | W4 | AI-mode rule routing and chat | AI + frontend | Not started | M | T028,T030,T031,T039 | R015,R019,R023,R056,R067,R074,R083,R085,R093 | Route rule-origin actions through evaluator in AI mode and chat through same proposal graph. | No backdoor chat recommendation, no silent mode switch, timeout misses remain visible. | Waiting
T041 | W4 | Simulation and virtual portfolios | Quant + backend | Not started | M | T018,T026,T034,T035 | R017,R049,R063,R064,R082,R089,R090,R098 | Implement virtual capital, virtual order/fill policy, partial/no fills, slippage/fees and lifecycle events. | Same-bar ambiguity, dividend/split/assignment, real/sim segregation and no broker calls. | Waiting
T042 | W4 | Benchmark and attribution workspace | Quant + frontend | Not started | M | T018,T033,T041 | R042,R043,R064,R065,R084,R090,R098,R099 | Implement preselected baseline versions and cash-flow-matched actual/sim scorecards. | Deposits not returns; no reconstructed historical trades from holdings snapshots. | Waiting
T043 | W5 | Feedback and improvement evidence | AI + backend | Not started | M | T036,T039,T041 | R028,R029,R031,R040,R052,R084,R087 | Capture errors, user feedback, private evaluation cases and permitted outcome categories. | Dismissal not assumed losing trade; private feedback not global training consent. | Waiting
T044 | W5 | Experiment orchestrator and assessor | AI + platform | Not started | M | T007,T032,T037,T043 | R028,R029,R030,R032,R033,R035,R037,R084,R092,R099 | Implement candidate lineage, task-specific scorecards, independent assessor and experiment budget scheduling. | Candidates cannot change test access, risk constraints, acceptance thresholds or approval records. | Waiting
T045 | W5 | Personal adaptation improvement path | AI engineer | Not started | L | T044 | R028,R031,R033,R039,R040,R084 | Implement candidate changes to alert/explanation preference configuration with reversible private state. | Helpful fixture improvement plus deliberate regression rejection; no widening investment policy. | Waiting
T046 | W5 | Research/retrieval improvement path | AI engineer | Not started | L | T044,T036 | R028,R029,R033,R040,R084 | Implement extraction/query/prompt candidate generation and controlled evaluation/promotion. | Publication-date fixture improves while a false fact/reference regression is rejected. | Waiting
T047 | W5 | Strategy/model improvement path | Quant + AI | Not started | L | T033,T044 | R028,R029,R033,R034,R059,R065,R084,R099 | Implement bounded strategy/ranking candidates, trial accounting, prospective review and adoption artifacts. | Overfit higher-P&L candidate with violations rejected; user adoption required for semantics. | Waiting
T048 | W5 | Evaluator improvement path | AI engineer | Not started | L | T039,T044 | R028,R029,R030,R033,R039,R084,R092,R099 | Implement candidate evaluator policies assessed by separate fixed evaluation control. | False-approval/overrejection/latency/cost metrics and protected answer-key tamper rejection. | Waiting
T049 | W5 | Sandboxed code improvement path | Security + AI engineer | Not started | L | T007,T044 | R028,R030,R033,R038,R039,R076,R086,R092,R099 | Generate reviewed code patches in immutable sandbox inputs; test, package and route human release approval. | No host/secret/prod writes; test-improving and malicious candidate negative controls. | Waiting
T050 | W5 | Recursive optimizer improvement path | AI + verifier | Not started | L | T044,T049 | R028,R030,R033,R037,R038,R076,R086,R092,R099 | Implement optimizer V0 to V1 self-change with independent assessment and actual V1 next-cycle execution. | Version receipts and subsequent lineage prove recursion; no self-certification or relabelled repeated prompting. | Waiting
T051 | W5 | Release signing adoption and rollback | Platform + security | Not started | M | T027,T044 | R030,R034,R039,R051,R076,R087,R092,R096,R099 | Implement candidate-to-release signing, operator install, user strategy adoption and compatible rollback. | Maintainer signature not user adoption; unsupported rollback pauses without rewriting records. | Waiting
T052 | W5 | Private learning export/delete controls | Privacy + backend | Not started | M | T043,T045,T051 | R031,R039,R051,R052,R087,R096 | Implement learned-state classification, consent revocation, data lineage invalidation and safe export/import. | No executable activation/credential export; deleted evidence no longer marked reproducible. | Waiting
T053 | W6 | Dashboard and policy/reconciliation UI | Frontend engineer | Not started | M | T019,T024,T026 | R002,R016,R042,R043,R047,R056,R068,R082,R093 | Build account/portfolio/decision views with scope/freshness/qualification and accessible numerical controls. | Keyboard-only essential journeys and contradictory/stale/pending states visible. | Waiting
T054 | W6 | Research/options/simulation UI | Frontend engineer | Not started | M | T035,T040,T041,T042 | R017,R019,R020,R056,R063,R064,R065,R084,R085,R089,R090,R093,R098,R099 | Build evidence drilldown, options scenarios, virtual mode and differentiated scorecards. | No uncertainty hidden behind color or model confidence; sim labels persist across navigation. | Waiting
T055 | W6 | Improvement and governance UI | Frontend engineer | Not started | M | T045,T046,T047,T048,T049,T050,T051 | R028,R030,R033,R034,R037,R056,R092,R093,R099 | Build all six improvement dashboards with scorecards, approval separation and lineage/rollback controls. | Full recursive demonstration inspectable; forbidden roles cannot promote. | Waiting
T056 | W6 | Notifications and current-state resolution | Backend + frontend | Not started | M | T024,T025,T026 | R020,R047,R067,R069,R083,R085,R093 | Implement in-app feed, email/provider-neutral SMTP, browser push qualification, preferences and dedupe. | Financial details minimal; late notification opens expired state; sending is not read receipt. | Waiting
T057 | W6 | Hosted/self-hosted portability | Platform + backend | Not started | M | T015,T017,T052,T055 | R006,R013,R036,R051,R052,R087,R096,R097 | Implement manifest export/import, compatible state migration and reconnect procedure. | Round-trip preserves compatible state and reports omitted licensed evidence; zip traversal/secret tests. | Waiting
T058 | W6 | Privacy retention and recovery tombstones | Privacy + platform | Not started | M | T052,T057 | R031,R052,R075,R077,R086,R087,R088 | Implement retention classes, deletion jobs, legal holds, backup expiry and restore-time tombstone application. | Deletion/reproducibility UX and no reappearance after restoring old backup. | Waiting
T059 | W6 | Hosted service and billing boundary | Platform + product | Not started | M | T003,T010,T053 | R001,R006,R007,R055,R075,R086,R087,R097 | Implement managed-service entitlement separate from financial ranking, provider billing and application independence. | Cancel/export flows; hosted billing cannot grant broker privileges or corrupt objective rankings. | Waiting
T060 | W7 | Container profiles and operations | Platform engineer | Not started | M | T009,T007,T051,T057 | R006,R013,R036,R054,R076,R077,R088,R092,R096,R097 | Package supported local/hosted profiles with health, secrets, backups, resource quotas and upgrade docs. | No vendor call required for self-hosting; full sandbox profile actually qualified. | Waiting
T061 | W7 | Load latency and quota qualification | Performance engineer | Not started | L | T022,T025,T040,T050,T056,T060 | R014,R027,R032,R035,R054,R067,R077,R083,R088 | Exercise 100 monitored users/20 sessions, imports, simulations and bounded experiments with actual timing instrumentation. | 5s/15s/60s metrics include misses; account freshness and provider quota are separately recorded. | Waiting
T062 | W7 | Security and supply-chain assessment | Security reviewer | Not started | M | T016,T037,T049,T050,T058,T060 | R005,R018,R021,R038,R051,R052,R075,R076,R086,R087,R092,R094,R095,R096 | Run cross-tenant, SSRF, CSV/archive injection, dependency, credential, sandbox and signing tests. | Critical control failures block release; reports contain reproducible evidence and no exposed secrets. | Waiting
T063 | W7 | Backup restore and incident drills | Operations engineer | Not started | M | T058,T060 | R020,R052,R069,R077,R085,R087,R088 | Run restore, provider outage, wrong-price correction, credential revocation and worker-crash drills. | Measured RPO/RTO, tombstones and affected proposal invalidation with visible service impact. | Waiting
T064 | W7 | Free baseline and full-scope E2E qualification | Independent verifier | Not started | L | T015,T016,T033,T035,T040,T041,T042,T050,T055,T057,T061,T062,T063 | R003,R006,R008,R017,R018,R033,R037,R053,R059,R062,R063,R064,R065,R078,R084,R089,R090,R092,R095,R098,R099 | Execute all release journeys on supported deployments and permitted live/provider/synthetic evidence categories. | No mandatory family/connector/recursive path silently disabled; specific free floor and qualified paid intraday/options configuration pass. | Waiting
T065 | W7 | Commercial and open-source release review | Owner + legal + security | Not started | M | T002,T003,T059,T064 | R001,R007,R021,R022,R041,R055,R079,R094,R095,R097 | Review permissions, legal coverage, notices, claims, contributors, support/economics and all gate receipts. | No docs-only or simulated evidence labelled commercial-ready/live profitable; unresolved mandatory gates block. | Waiting
T066 | W7 | Final agent handoff and operator guides | Technical writer + lead | Not started | M | T064,T065 | R013,R036,R041,R051,R056,R079,R087,R093,R094,R096,R097 | Publish exact install/check/recovery commands from executed environments, architecture map and known limitations. | Instructions reproduce on clean supported host; no fictional command, unresolved required placeholder or fabricated test pass. | Waiting

## Requirements
REQUIREMENTS & ACCEPTANCE
The normative statements and their acceptance outcomes remain traceable to the approved decisions.
Requirement | Decision lineage | Domain | Priority | Requirement statement | Acceptance criterion | Design status | Acceptance test
R001 | Q1 | product | Release required | Personal-first with near-term multi-user commercialization; preserve tenant and deployment foundations from the start. | Same core runs a private account and hosted tenants without converting global financial state into user state. | Specified - not implemented | AT001
R002 | Q2 | product | Release required | Primary purpose is portfolio-aware decisions plus frequent trading signals. | A decision identifies its goal/account impact; frequent scans do not bypass suitability. | Specified - not implemented | AT002
R003 | Q3 | data | Release required | A useful no-paid-market-data baseline must not require paid AI; hosting and optional providers are separate. | Rules-only onboarding and a qualified decision workflow complete with zero paid data and zero AI calls. | Specified - not implemented | AT003
R004 | Q4 | data | Release required | Mandatory discovery is US-listed stocks and ETFs with currency-aware accounts. | US instrument identity and CAD/USD accounting work; outside-scope holdings remain visible. | Specified - not implemented | AT004
R005 | Q5 | security | Release required | First release proposes specific actions but never submits, modifies or cancels broker orders. | Broker mutation routes/tools are absent and attempted mutations are blocked at connector boundaries. | Specified - not implemented | AT005
R006 | Q6 | platform | Release required | Both hosted and complete self-hosted editions are release requirements. | Both deployment profiles pass core journeys and isolation checks. | Specified - not implemented | AT006
R007 | Q7 | compliance | Release required | Initial commercial audience includes Canadian and US residents. | Jurisdiction inventory and counsel-approved capability matrix cover intended launch customers in both countries. | Specified - not implemented | AT007
R008 | Q8 | strategies | Release required | Intraday swing discovery plus optional same-day opportunities; no sub-minute scalping requirement. | Qualified regular-session strategy can produce timely proposals under its data/model configuration. | Specified - not implemented | AT008
R009 | Q9 | strategies | Release required | Frequent evaluation means timely qualifying changes, not a quota of trades. | A no-opportunity session records zero proposals and explicit rejection reasons without manufactured trades. | Specified - not implemented | AT009
R010 | Q10 | risk | Release required | Separate investing and trading allocations with portfolio-wide limits. | A trading proposal cannot spend a long-term reserve and combined exposure is checked. | Specified - not implemented | AT010
R011 | Q11 | data | Release required | Free mode may require a user-connected free provider account/key. | Setup discloses provider account, limits and rights; key connection alone does not mark capabilities qualified. | Specified - not implemented | AT011
R012 | Q12 | portfolio | Release required | Stale or unreconciled holdings/cash block affected portfolio-specific sizing. | A stale account yields research or hypothetical output, not confirmed buying-power sizing. | Specified - not implemented | AT012
R013 | Q13 | platform | Release required | Independent open-source core and complete self-hosted application; no mandatory vendor-operated service. | Disconnect vendor services and exercise permitted core workflows with user-selected dependencies. | Specified - not implemented | AT013
R014 | Q14 | data | Release required | Prioritized live monitoring plus broader scheduled discovery; tracked and streamed universes differ. | Exceeding live-symbol quota produces visible prioritization, not fictitious continuous coverage. | Specified - not implemented | AT014
R015 | Q15 | ai | Release required | Auditable rules and AI research both originate proposals; a separate agent evaluates actionable AI-mode proposals. | An AI-only thesis can qualify without a technical trigger, but cannot bypass hard checks. | Specified - not implemented | AT015
R016 | Q16 | onboarding | Release required | MCQs and necessary numeric/date inputs propose a policy/strategy shortlist for explicit runtime approval. | Contradictory objectives require resolution and no policy is active merely from inferred answers. | Specified - not implemented | AT016
R017 | Q17 | options | Release required | Opt-in first-release options include long calls/puts, covered calls, cash-secured puts and defined-risk verticals. | All permitted structures have scenarios and checks; out-of-scope imported contracts remain represented. | Specified - not implemented | AT017
R018 | Q18 | ai | Release required | API and subscription access use provider-specific officially permitted routes and deployment qualification. | No session-token interception/proxy; unavailable subscription routes are reported, not emulated. | Specified - not implemented | AT018
R019 | Q19 | ai | Release required | Mandatory evidence/calculation verification is tiered; separate model review is required for AI-mode actions. | Factual alerts can pass without LLMs; pending AI review cannot be relabelled as reviewed. | Specified - not implemented | AT019
R020 | Q20 | proposals | Release required | Action proposals expire and have invalidation conditions plus preserved version history. | Late notifications resolve to current state; corrected decisions do not overwrite original results. | Specified - not implemented | AT020
R021 | Q21 | compliance | Release required | Commercial legal and provider-rights clearance are release gates. | Documentation access and disclaimers do not mark rights/regulatory gates passed. | Specified - not implemented | AT021
R022 | Q22 | platform | Release required | Apache-2.0 is the selected application license, superseding AGPL proposals. | License and dependency inventory reflect Apache choice without bundling incompatible material by assumption. | Specified - not implemented | AT022
R023 | Q23 | ai | Release required | Support audited rules-only and AI-enabled modes; evaluator covers both proposal origins in AI mode. | Switching modes is explicit; rule outputs are not falsely labelled AI-reviewed. | Specified - not implemented | AT023
R024 | Q24 | research | Release required | AI proposals qualify through evaluated research workflows and proposal-specific checks, not necessarily a backtested rule. | Workflow status/version is recorded and model changes do not silently inherit evidence. | Specified - not implemented | AT024
R025 | Q25 | ai | Release required | Evaluator is a separate run/context; a different model family is optional and empirically justified. | Configuration reports same-model isolation versus cross-model diversity accurately. | Specified - not implemented | AT025
R026 | Q26 | ai | Release required | Material factual/evidence conflicts and hard risk failures block; forecast differences may be disclosed; revisions bounded. | Reviewer disagreement cannot be bypassed by repeated sampling until an approval appears. | Specified - not implemented | AT026
R027 | Q27 | ai | Release required | Frequent deterministic monitoring; AI on meaningful events/schedules/requests within budgets and deadlines. | Unchanged evidence is reused lawfully; quota exhaustion cannot remove mandatory review. | Specified - not implemented | AT027
R028 | Q28 | improvement | Release required | All six improvement targets are in scope, including code and the optimizer itself. | Each target has a candidate/evaluation/review/promotion/rollback path. | Specified - not implemented | AT028
R029 | Q29 | improvement | Release required | Promotion uses predeclared scorecards with hard risk/privacy/evidence constraints, not recent returns alone. | A candidate with higher simulated P&L but a hard violation is rejected. | Specified - not implemented | AT029
R030 | Q30 | improvement | Release required | Autonomous authorized experiments, human-controlled promotion of investment-affecting or code changes. | A model cannot self-approve its deployment or widen permissions. | Specified - not implemented | AT030
R031 | Q31 | privacy | Release required | Private learning per user/installation by default; cross-user use requires separate consent and permitted data. | Another tenant cannot access or learn from private examples absent authorized transformation/consent. | Specified - not implemented | AT031
R032 | Q32 | improvement | Release required | Separate experiment resource budgets; current monitoring and verification take priority. | Experiment exhaustion pauses experiments while essential services remain available. | Specified - not implemented | AT032
R033 | Q33 | improvement | Release required | All six improvement areas, code-level change and recursive optimizer change must work at first release. | Full release cannot pass by labelling code/recursive paths future work or disabling them. | Specified - not implemented | AT033
R034 | Q34 | governance | Release required | Material changes to enabled investment strategies require user adoption after release approval. | Maintainer approval does not silently change an existing user's strategy semantics. | Specified - not implemented | AT034
R035 | Q35 | operations | Release required | Personal pilot incremental inference ceiling USD100/month; improvement maximum 20 percent (USD20). | Concurrent reservations cannot exceed either cap; unrelated subscription/hosting expenses are separately shown. | Specified - not implemented | AT035
R036 | Q36 | platform | Release required | Single-machine container self-hosting without required Kubernetes/GPU/vendor service. | Clean supported installation, backup restore and core workflows complete on qualified hardware. | Specified - not implemented | AT036
R037 | Q37 | improvement | Release required | Demonstrate V0 optimizer proposing V1, independent evaluation, human promotion, then V1 running next cycle. | Lineage and actual version receipts prove changed implementation was used, including rejected controls. | Specified - not implemented | AT037
R038 | Q38 | security | Release required | Generated code is isolated from production secrets, DB writes, unrestricted network and host control. | Sandbox escape/secret/egress tests fail closed with no weaker silent fallback. | Specified - not implemented | AT038
R039 | Q39 | improvement | Release required | User learning is tenant-scoped; shared executable/optimizer changes are installation/release scoped. | Hosted user cannot deploy a private executable fork into shared production. | Specified - not implemented | AT039
R040 | Q40 | research | Release required | Open evaluation framework and permitted starter corpus; distinguish synthetic/historical/prospective evidence. | Starter demonstrations never count as live trading evidence or personal learned history. | Specified - not implemented | AT040
R041 | Q41 | product | Release required | Full scope and release gates take precedence over launch date; budget limits throughput rather than silently cutting scope. | Required capabilities actually complete representative workloads within qualified resource constraints. | Specified - not implemented | AT041
R042 | Q42 | portfolio | Release required | Partial portfolios allowed with scoped conclusions; outside-coverage assets retained with gaps. | Unknown outside exposure is not zero; full-financial-situation claims are withheld. | Specified - not implemented | AT042
R043 | Q43 | portfolio | Release required | Multiple accounts/currencies with account-specific spendability and consolidated risk. | Cash in another account/currency cannot fund a proposal without an explicit prerequisite. | Specified - not implemented | AT043
R044 | Q44 | risk | Release required | Stock/ETF proposals cash-funded long-only, nonleveraged/noninverse; approved options remain. | Short/leveraged discovery cannot become a new action; existing such positions still contribute known exposure. | Specified - not implemented | AT044
R045 | Q45 | evidence | Release required | Primary and permitted independent sources; optional social inputs clearly distinguished from facts. | An unverified social claim is a research lead, not corroborated evidence. | Specified - not implemented | AT045
R046 | Q46 | portfolio | Release required | Tax-relevant records and warnings, not a comprehensive tax engine or automated tax-loss harvesting. | P&L/cost basis provenance is shown without presenting it as definitive tax liability. | Specified - not implemented | AT046
R047 | Q47 | ux | Release required | Responsive web, in-app feed, configurable email/browser push; no native mobile/SMS launch requirement. | Expiry-aware notifications work and self-hosting needs no proprietary notification server. | Specified - not implemented | AT047
R048 | Q48 | integrations | Release required | Small named set of tested read-only broker sync routes; CSV/manual fallback. | Each connector passes fields, pagination, reconnect and reconciliation tests, not only login. | Specified - not implemented | AT048
R049 | Q49 | risk | Release required | Proposals form jointly feasible sets with explicit alternatives and internal capital commitments. | Two USD4000 proposals cannot jointly consume USD5000; unexecuted sales do not create cash. | Specified - not implemented | AT049
R050 | Q50 | strategies | Release required | Initial actionable intraday proposals are regular-session only; research may run outside session. | Premarket event can create conditional research but must be refreshed before activation. | Specified - not implemented | AT050
R051 | Q51 | privacy | Release required | Hosted/self-hosted migration is supported at first release. | Compatible financial/policy/private-learning state transfers; credentials and executable imports do not activate silently. | Specified - not implemented | AT051
R052 | Q52 | privacy | Release required | Tamper-evident retained history, not indefinite private retention; explicit correction/deletion/backups. | Deleted evidence makes replay limitations visible and restoration reapplies tombstones. | Specified - not implemented | AT052
R053 | Q53 | integrations | Release required | CIBC import, Questrade/IBKR read-only sync, plus Wealthsimple sync and Yahoo CSV interoperability. | Named commitments each have deployment-specific qualification evidence; no silent downgrade to generic CSV. | Specified - not implemented | AT053
R054 | Q54 | operations | Release required | Reference scale: 10 accounts, 250 instruments, 100000 records/user; hosted 100 users and 20 concurrent sessions. | Combined workload tests retain background monitoring for all users and distinguish provider stream limits. | Specified - not implemented | AT054
R055 | Q55 | product | Release required | Managed service pricing plus user-connected providers; independent self-hosted core and unbiased rankings. | Billing/affiliate data cannot influence security rankings; cancelling hosting supports lawful export. | Specified - not implemented | AT055
R056 | Q56 | ux | Release required | Dashboard-led portfolio/decision/research/governance workspaces; chat uses same verified state. | Chat cannot emit an actionable recommendation outside the governed proposal pipeline. | Specified - not implemented | AT056
R057 | Q57 | integrations | Release required | Yahoo tested CSV portfolio/watchlist import and compatible export; no auto-sync/data-adapter launch promise. | Round-trip differences are shown and Yahoo watchlists never imply owned shares. | Specified - not implemented | AT057
R058 | Q58 | portfolio | Release required | Underlying accounts and data sources are separate; reconcile overlapping views without duplication. | A broker position mirrored in Yahoo totals once; two real accounts remain distinct. | Specified - not implemented | AT058
R059 | Q59 | strategies | Release required | All six versioned stock/ETF strategy families required; qualification status separate from catalogue inclusion. | Each family has documented logic/evaluation; failed variants remain research-only without edge claims. | Specified - not implemented | AT059
R060 | Q60 | risk | Release required | Conservative liquidity/spread/data/status-screened universe; optional speculative research cannot bypass gates. | OTC/penny/failed checks excluded from default actionable discovery while existing exposure remains tracked. | Specified - not implemented | AT060
R061 | Q61 | strategies | Release required | Bounded versioned strategy configuration, not unrestricted hosted arbitrary-code or visual strategy builder. | Configuration changes enter relevant validation/adoption; developer code extension remains controlled. | Specified - not implemented | AT061
R062 | Q62 | strategies | Release required | Free baseline supports portfolio-specific rebalancing plus a qualified non-intraday long-only strategy. | End-to-end free positive and abstention journeys pass, not only dashboards/alerts. | Specified - not implemented | AT062
R063 | Q63 | simulation | Release required | User-facing application-managed virtual portfolios and optional approved-policy shadow tracking. | Simulation never changes real cash and clearly labels fills, costs, assumptions and unsupported cases. | Specified - not implemented | AT063
R064 | Q64 | analytics | Release required | Versioned goal-appropriate/cash-flow-matched benchmarks and separate actual/simulated/recommendation scorecards. | No fabricated historical cash flows; TWR/MWR calculated only with sufficient inputs. | Specified - not implemented | AT064
R065 | Q65 | research | Release required | Separate operational qualification, investment evidence and user eligibility; family-specific actionable-use gates. | Limited investment evidence allowed only under predeclared human-approved policy, never an ad-hoc exception. | Specified - not implemented | AT065
R066 | Q66 | data | Release required | Versioned feed specifications and qualified continuity/reinitialization for provider changes. | A mid-session IEX/SIP change cannot continue the old range silently; recovered signals are retrospective. | Specified - not implemented | AT066
R067 | Q67 | operations | Release required | Targets: 95 percent factual events within 5s of receipt; rules-only within 15s; AI intraday deadline at most 60s or earlier expiry. | Independent event-age and remaining-window checks; misses count, retries cannot reset trigger, delivery measured separately. | Specified - not implemented | AT067
R068 | Q68 | risk | Release required | Explicit approved numerical account/allocation/concentration/planned-loss/scenario limits for sizing. | Denominators and currencies displayed; missing mandatory limits block sizing; stops are not loss guarantees. | Specified - not implemented | AT068
R069 | Q69 | risk | Release required | Scoped loss/drawdown triggers pause new risk; monitoring and checked risk reduction continue; controlled resumption. | Deposits cannot erase breaches; material resume needs reconciled state and explicit acknowledgement. | Specified - not implemented | AT069
R070 | Q70 | architecture | Release required | Typed Python core, TypeScript/React, PostgreSQL, analytical file/object storage and durable jobs; three authority paths. | Live, experiment and release operations share contracts but cannot share unrestricted authority. | Specified - not implemented | AT070
R071 | Q71 | portfolio | Release required | Reconciled decimal journal with explicit effective/publication/receipt/decision times; one calculation contract. | Source corrections update current reconstruction without rewriting historical knowledge. | Specified - not implemented | AT071
R072 | Q72 | strategies | Release required | Interpretable six-family starting implementations; 6-month/200-day momentum and 15-minute ORB are unqualified research defaults. | Parameter choices are labelled candidates and cannot auto-enable live strategies. | Specified - not implemented | AT072
R073 | Q73 | integrations | Release required | Capability/rights/degraded-state registry; provider/entitlement changes require reassessment. | Connected status does not imply qualified; tenant feed sharing requires rights and consent. | Specified - not implemented | AT073
R074 | Q74 | ai | Release required | Persisted bounded workflows, explicit model/runtime versions, no silent paid/provider fallback. | One evaluation plus at most one permitted revision; deadline/claim checks rerun on change. | Specified - not implemented | AT074
R075 | Q75 | security | Release required | Read-only operation allowlists, secrets outside agents, tenant isolation including nonowner/nonbypass DB roles. | Cross-tenant, RLS-bypass, tool mutation and secret-exfiltration tests block release. | Specified - not implemented | AT075
R076 | Q76 | improvement | Release required | gVisor initial Linux sandbox qualification target; full recursive scope; reviewed signed promotion and compatible rollback. | Unsupported sandbox cannot qualify full release by dropping mandatory improvement paths. | Specified - not implemented | AT076
R077 | Q77 | operations | Release required | Hosted targets 99.9 percent availability, 15-minute RPO and 4-hour RTO; receipts not guarantees. | Recovery and combined-budget tests demonstrate targets while external/end-to-end failures stay visible. | Specified - not implemented | AT077
R078 | Q78 | testing | Release required | End-to-end release journeys cover free mode, overlap, AI, intraday, options, risk pause, simulation, improvement, migration and isolation. | All required journeys tied to versioned execution evidence, including negatives and failure recovery. | Specified - not implemented | AT078
R079 | Q79 | governance | Release required | Separate design choices from factual provider/legal/security/performance/economic gates. | No completion claim without versioned evidence and no silent scope reduction when a gate fails. | Specified - not implemented | AT079
R080 | Q70,Q71 | architecture | Release required | All API monetary amounts/quantities use decimal strings; times use UTC with exchange calendar identity. | Schema rejects binary numeric money and timestamps without offsets. | Specified - not implemented | AT080
R081 | Q58,Q71 | portfolio | Release required | Immutable source observations map into balanced postings or quarantined exceptions; provisional views never double-post. | Journal balance, idempotency, correction reversal and lot/cash reconciliation fixtures pass. | Specified - not implemented | AT081
R082 | Q12,Q49,Q68 | risk | Release required | Final publication atomically binds policy, account and proposal-set revisions to a checked cash commitment. | A competing account update causes re-evaluation, never time-of-check/time-of-use overspend. | Specified - not implemented | AT082
R083 | Q12,Q66,Q67 | data | Release required | Separate price, fundamental, calendar, broker and FX freshness policies; record event age and ingestion delay. | Fast processing of five-minute-old broker state never labels it real-time confirmed. | Specified - not implemented | AT083
R084 | Q24,Q29,Q40,Q65 | research | Release required | Track all experiments, point-in-time universe membership, delistings, corporate actions, costs and test access. | A future filing, present-day survivor list or repeated final-holdout feedback cannot qualify a strategy. | Specified - not implemented | AT084
R085 | Q19,Q20,Q74 | ai | Release required | Expose structured audit rationale and evidence, not require inaccessible private model chain of thought. | A reviewer can validate claim/calc provenance without requesting hidden model reasoning. | Specified - not implemented | AT085
R086 | Q26,Q38,Q75 | security | Release required | Freshness/eligibility/policy/legal/release controls are enforced outside LLM contexts. | Prompt injection asking to remove checks cannot change the final validator outcome. | Specified - not implemented | AT086
R087 | Q51,Q52,Q75 | privacy | Release required | Evidence-derived state is deleted or invalidated under policy; archive import is not arbitrary execution. | Malicious archive paths, symlinks, oversized extraction and executable payloads are rejected. | Specified - not implemented | AT087
R088 | Q70,Q77 | operations | Release required | At-least-once delivery uses idempotent consumers, bounded leases/retries and dead-letter recovery. | Worker crash after database commit does not duplicate holdings or send duplicate actionable alerts. | Specified - not implemented | AT088
R089 | Q17 | options | Release required | Option contract deliverables, adjusted multipliers, exercise style and settlement are explicit, not defaulted blindly. | Nonstandard/unknown contracts remain represented but unsupported sizing/payoffs are blocked. | Specified - not implemented | AT089
R090 | Q64 | analytics | Release required | No-unique-root MWR, nonpositive equity and missing valuation intervals return explicit unavailable status. | Return fixtures identify ambiguity rather than invent a percentage. | Specified - not implemented | AT090
R091 | Q50,Q66 | data | Release required | Exchange sessions include holidays, DST, early closes, auctions and halts in versioned calendars. | ORB and expiry deadlines are session-derived rather than fixed UTC strings. | Specified - not implemented | AT091
R092 | Q30,Q37,Q38,Q76 | security | Release required | Public/community code and skill inputs are reviewed; the optimizer cannot replace protected gates or signing keys. | Mutation of evaluator answer keys, final thresholds or human authorization fails integrity checks. | Specified - not implemented | AT092
R093 | Q47,Q56 | ux | Release required | Keyboard-accessible financial tables and text states accompany colors; screen freshness is continuously visible. | Keyboard-only and screen-reader journeys cover policy, reconciliation and proposal expiry. | Specified - not implemented | AT093
R094 | Q21,Q73,Q79 | governance | Release required | All external-provider feature claims are dated and distinguish docs, permission, auth and workload evidence. | A docs-only record cannot become commercial-qualified without required receipts. | Specified - not implemented | AT094
R095 | Q18,Q21 | ai | Release required | Provider use permission includes financial-advice policy, allowed tools, retention and training settings. | Unsupported financial-use route is blocked even when OAuth or inference works. | Specified - not implemented | AT095
R096 | Q13,Q36,Q51 | operations | Release required | Self-hosted proof uses operator-controlled backup keys and no embedded universal service credentials. | Install and restore work without project-vendor account or secret bootstrap call. | Specified - not implemented | AT096
R097 | Q1,Q13 | product | Release required | Repository branding and production domain remain owner-configurable; no invented identity is normative. | Brand replacement changes metadata only, not contracts or workflow semantics. | Specified - not implemented | AT097
R098 | Q63,Q64 | simulation | Release required | A simulated fill must occur after modeled submission and under a declared available-data convention. | Same-bar ambiguity resolves conservatively or as indeterminate, never automatically best-case. | Specified - not implemented | AT098
R099 | Q30,Q34,Q65 | governance | Release required | Runtime approvals are typed by maintainer release, operator install and user strategy adoption; planning delegation is not runtime consent. | A conversational yes cannot satisfy a production promotion or investment-policy signature. | Specified - not implemented | AT099

## Gates
RELEASE EVIDENCE GATES
All gates begin unverified. Passing artifact checks does not clear product, legal, provider, quant, security or operational gates.
Gate | Domain | Gate definition | Required evidence | Status | Evidence receipt | Owner | Release blocking
G01 | Architecture | Independent hosted and self-hosted core | Clean-install receipts for both profiles, no proprietary core dependency, Apache/dependency inventory | Not verified |  | Architecture lead | Yes
G02 | Data | Free-data usefulness and rights | Permitted use confirmation plus actual quota/coverage/freshness tests and free end-to-end actionable/abstention workflow | Not verified |  | Data lead | Yes
G03 | Integrations | Named brokerage and Yahoo/CIBC compatibility | Deployment-specific auth/field/reconnect/reconciliation/round-trip results for every required integration | Not verified |  | Integrations lead | Yes
G04 | Compliance | Canada and US commercial authority | Qualified product-specific jurisdiction/registration/exemption/privacy/marketing review and required approvals | Not verified |  | Compliance lead | Yes
G05 | Accounting | Journal reconciliation and numerical integrity | Independent fixtures, property tests, source-overlap and cash/concurrency tests with exact revisions | Not verified |  | Accounting lead | Yes
G06 | Quant | All six strategy families and evidence policies | Versioned implementations, predeclared family gates, no fabricated edge, qualified free and intraday paths | Not verified |  | Quant lead | Yes
G07 | Options | Qualified opt-in options capability | Contract/deliverable/payoff/assignment/collateral tests and qualified live-data path; free indicative restrictions | Not verified |  | Options lead | Yes
G08 | AI | API and permitted subscription routes | Provider-specific auth/use permission and measured structured/review performance per supported configuration | Not verified |  | AI lead | Yes
G09 | Decision safety | Proposal authority and risk controls | No broker mutations, atomic cash/policy checks, expiry, scoped pauses and explicit resumption tests | Not verified |  | Decision safety lead | Yes
G10 | Improvement | All six improvement paths including recursion | Positive/negative tests, independent assessment, V0→V1→next cycle, promotion/adoption/rollback receipts | Not verified |  | Improvement lead | Yes
G11 | Security | Tenant/agent/sandbox isolation and supply chain | Cross-tenant, credential, SSRF, injection, sandbox, signing and archive adversarial results; unresolved criticals zero | Not verified |  | Security lead | Yes
G12 | Privacy | Consent, export, deletion, migration and retention | Private learning isolation, safe round trip, licensed omissions, tombstone restore and backup-expiry demonstration | Not verified |  | Privacy lead | Yes
G13 | Simulation | Virtual execution and benchmark integrity | Fill/cost/ambiguity/corporate-action tests, cash-flow matched baseline and separate actual/sim scorecards | Not verified |  | Simulation lead | Yes
G14 | Operations | Load latency budget and recovery | Combined stated workload, P95 timings plus misses, per-source age, USD100/USD20 caps and measured RPO/RTO | Not verified |  | Operations lead | Yes
G15 | UX | Accessible truthful operational experience | Keyboard/screen-reader workflows, visible scope/freshness/qualification, expiry-aware notifications and chat governance | Not verified |  | UX lead | Yes
G16 | Release | Full-scope release and claims review | All mandatory gates, support/runbooks, notices, provider/legal renewal dates and independent final verifier signoff | Not verified |  | Release lead | Yes

## Qualifications
EXTERNAL & TECHNICAL QUALIFICATION
Documentation evidence is not actual account testing, financial-use permission, legal clearance or measured operational fitness.
Check | Capability | Owner | Tasks | Current evidence status | Scope | Qualification requirement | Required receipt | Source IDs | Source URLs
QUAL01 | Alpaca free workload | Integration lead | T002,T004,T021,T022 | Documentation checked; operational qualification not run | Both | Prove 30-stream prioritized tracking plus scheduled discovery, explicit IEX/SIP feed semantics, quotas and action-capable free EOD strategy. | Actual permitted credentials, dates, measured events, accuracy and missing-data receipts. | SRC-01,SRC-02 | https://docs.alpaca.markets/us/docs/about-market-data-api ¦ https://docs.alpaca.markets/us/docs/market-data-faq
QUAL02 | Alpaca hosted data rights | Owner + counsel | T002,T065 | Permission pending | Hosted commercial | Obtain product-specific display, storage, multiuser, redistribution and model-processing permissions. BYO does not pool rights. | Written permitted-use/entitlement matrix. | SRC-01 | https://docs.alpaca.markets/us/docs/about-market-data-api
QUAL03 | CIBC authentic CSV | Integration lead | T005,T015 | Actual export sample missing | Both | Validate real exported holdings/activity, encodings, sign and fee semantics. CSV only promised. | Sanitized approved samples + golden parse/reconciliation tests. | SRC-26 | Library: Codex_AC_ECC_Setup.md, 2026-10-06
QUAL04 | Yahoo CSV interchange | Integration lead | T005,T015 | Official search excerpt checked; sample missing | Both | Read supported portfolio/watchlist fields, distinguish mirrors, export compatible current template; no automatic sync promise. | Actual import/export roundtrip screenshots/results and version. | SRC-09 | https://help.yahoo.com/kb/finance-for-web/download-portfolio-data-yahoo-finance-sln15034.html
QUAL05 | Questrade personal and hosted sync | Integration lead | T002,T005,T016 | Documentation checked; credentials/permissions untested | Both | Read-only positions, cash, transactions, options, revocation and history; select direct or approved aggregator per deployment. | Provider approval + test account end-to-end reconciliation. | SRC-06,SRC-04,SRC-05 | https://www.questrade.com/api ¦ https://docs.snaptrade.com/docs/broker-access-guide ¦ https://docs.snaptrade.com/docs/trade-detection
QUAL06 | IBKR personal and third-party sync | Integration lead | T002,T005,T016 | Third-party approval and integration tests pending | Both | Qualify actual authentication/session/account types; no assumption one consumer flow covers hosted SaaS. | Approved app flow + account/history/options/failure receipts. | SRC-07,SRC-04 | https://www.interactivebrokers.com/campus/ibkr-api-page/webapi-doc/ ¦ https://docs.snaptrade.com/docs/broker-access-guide
QUAL07 | Wealthsimple synchronization | Integration lead | T002,T005,T016 | Aggregator candidate documented; operational tests pending | Both | Test actual balances/positions/transactions/options and delay; fallback CSV not replacement for required sync. | Read-only flow, measured lag incl >=5min detection assumption and reconciliation. | SRC-04,SRC-05,SRC-08 | https://docs.snaptrade.com/docs/broker-access-guide ¦ https://docs.snaptrade.com/docs/trade-detection ¦ https://help.wealthsimple.com/hc/en-ca/articles/39449252453019-View-your-account-activity-and-running-balance
QUAL08 | Options execution-quality feed | Quant + integration | T021,T034,T035 | Not qualified | Configured options path | OPRA/other entitled suitable chain, contract terms, spreads, freshness and assignment lifecycle; indicative not auto-qualified. | Feed rights + contract-case and freshness tests. | SRC-01,SRC-20,SRC-21 | https://docs.alpaca.markets/us/docs/about-market-data-api ¦ https://www.optionseducation.org/referencelibrary/faq/options-assignment ¦ https://www.optionseducation.org/strategies/all-strategies/bear-put-spread
QUAL09 | SEC facts point-in-time | Data engineer | T023,T032 | Documentation checked; normalization untested | Both | Respect public limits/identification; handle taxonomy/units/amendments, availability timestamps and missing sectors. | Versioned facts corpus with expected publication and revision behavior. | SRC-10 | https://www.sec.gov/search-filings/edgar-application-programming-interfaces
QUAL10 | Bank of Canada reference FX | Data engineer | T023,T018 | Documentation checked; implementation untested | Both | Daily reference rates only; weekend/holiday stale policy; no executable FX claim. | Rate direction/unit/date tests and source rights review. | SRC-11 | https://www.bankofcanada.ca/valet-api-how-to/
QUAL11 | OpenAI API financial workflow | AI + compliance | T006,T037,T065 | Product permission/model capability not qualified | Both | Qualify current API model structured outputs, data terms, allowed financial use and cost controls independently of subscription. | Model/usage-policy matrix + sample task receipts. | SRC-12 | https://help.openai.com/en/articles/20001542-using-your-chatgpt-plan-in-other-apps-and-sites
QUAL12 | ChatGPT subscription integration | AI integration | T006,T037 | Participation/eligibility pending | Provider-supported configurations | Use approved participating-app/native route; eligible account/model/limits differ. No generic API credits claim. | Actual permitted sign-in and bounded request/limit test per edition. | SRC-12 | https://help.openai.com/en/articles/20001542-using-your-chatgpt-plan-in-other-apps-and-sites
QUAL13 | Anthropic API/native subscription | AI integration | T006,T037 | Native legal boundary checked; runtime untested | Provider-supported configurations | API and unmodified native runtime isolated; no collection of Claude.ai tokens/session credentials; financial use permitted. | Approved runtime workflow with keys hidden and rate/limit test. | SRC-13 | https://code.claude.com/docs/en/legal-and-compliance
QUAL14 | xAI API integration | AI integration | T006,T037 | API documentation checked; runtime untested | Both with API access | Qualify API capabilities, privacy, financial-use terms and metering; no consumer subscription promise. | Model/run/cost/timeout/citation JSON tests. | SRC-14 | https://docs.x.ai/developers/rest-api-reference/management/auth
QUAL15 | Free-mode strategy floor | Quant lead | T004,T027,T028,T030,T033,T064 | Not evaluated | Both | Rebalance and at least one non-intraday qualified rules-only strategy demonstrably work with permitted free data and no paid AI. | Positive/abstention/rejection cases, protocol and prospective evidence. | SRC-01,SRC-02,SRC-22 | https://docs.alpaca.markets/us/docs/about-market-data-api ¦ https://docs.alpaca.markets/us/docs/market-data-faq ¦ https://scholarworks.wmich.edu/math_pubs/42/
QUAL16 | Intraday signal and source fitness | Quant + performance | T031,T061 | Not evaluated | Suitable configured feed/account path | Actual same-day strategy must meet event freshness, account state, review and remaining action window. Document configurations that fail. | P95/timeout/miss reports including full denominator under load. | SRC-01,SRC-02,SRC-05 | https://docs.alpaca.markets/us/docs/about-market-data-api ¦ https://docs.alpaca.markets/us/docs/market-data-faq ¦ https://docs.snaptrade.com/docs/trade-detection
QUAL17 | gVisor and single-machine isolation | Security lead | T007,T049,T050,T060,T062 | Technology selected; deployment untested | Self-hosted and hosted experiment workers | No host Docker socket, production secrets, writable assessor, unapproved outbound network or live DB writes. | Adversarial breakouts/egress/permissions/resource tests in supported runtime. | SRC-16 | https://gvisor.dev/docs/
QUAL18 | Canadian commercial model | Qualified counsel | T003,T065 | Not legally assessed | Canada external users | Assess provinces, personalized securities advice, exemptions/registration/partner path, privacy and marketing. | Signed product-specific determination and controls. | SRC-17 | https://www.bcsc.bc.ca/industry/financial-technology-innovation/securities-law-fundamentals
QUAL19 | US commercial model | Qualified counsel | T003,T065 | Not legally assessed | US external users | Assess federal/state adviser issues, registration/exemptions, disclosures, performance, recordkeeping and data privacy. | Signed product-specific determination and controls. | SRC-18 | https://www.investor.gov/introduction-investing/general-resources/news-alerts/alerts-bulletins/investor-bulletins-45
QUAL20 | Model-assisted investment evidence | Quant + AI evaluation | T033,T038,T039,T044 | Not evaluated | All AI investment paths | No historical LLM leakage disguised as foresight; prospective baseline, calibrated grader, family-specific evidence gates. | Frozen inputs and comparative researcher/evaluator outcomes incl failures. | SRC-22 | https://scholarworks.wmich.edu/math_pubs/42/
QUAL21 | Recursive improvement and USD20 experiment budget | AI + platform | T044,T045,T046,T047,T048,T049,T050,T061 | Not evaluated | Both | All six real loops incl V0->V1 run within qualified resources; budget never used to omit required targets. | Measured complete experiments, protected assessment, promotion and rollback receipts. | SRC-16 | https://gvisor.dev/docs/
QUAL22 | Hosted security/load/recovery economics | Platform lead | T059,T060,T061,T062,T063 | Not measured | Hosted | 100 monitored users/20 sessions plus imported data and experiments; SLO,RPO,RTO, actual costs. | Load traces, restore drill, reconciled provider invoices, tenant tests. | SRC-15,SRC-16 | https://www.postgresql.org/docs/current/ddl-rowsecurity.html ¦ https://gvisor.dev/docs/
QUAL23 | Apache dependencies/source distribution | Maintainer | T001,T062,T065 | License chosen; dependency inventory not created | Open-source release | License compatibility/SBOM/NOTICE for runtime/dependencies; separate rights for datasets and third-party kits. | Legal review where needed plus SBOM and attribution audit. | SRC-23 | https://www.apache.org/licenses/LICENSE-2.0.txt
QUAL24 | User data migration/deletion | Privacy + platform | T052,T057,T058,T063 | Not tested | Both | Credential-free migration, compatibility review, private learned-state handling, deletions after backup restore and evidence unavailability. | Export roundtrip and restore+tombstone receipts. | SRC-26 | Library: Codex_AC_ECC_Setup.md, 2026-10-06

## Risks
RISK & MITIGATION REGISTER
Severity/likelihood are planning assessments. Mitigations are requirements, not controls already proven effective.
Risk | Description | Severity | Likelihood | Failure mode | Mitigation | Gate / task | Status
RISK01 | Commercial personalized-advice classification | Critical | Likely | No broker execution does not remove advice classification | Product-specific CA/US legal gates; restrict external release until cleared | G04,T003 | Open; mitigation untested
RISK02 | Free feed does not support strategy | High | Likely | IEX/limited history/rights fail declared research needs | Free qualification spike early; maintain explicit entitlement specs, no fake consolidated inputs | G02,T004 | Open; mitigation untested
RISK03 | Broker state lag invalidates sizing | Critical | Likely | Fast quotes hide delayed account state | Separate effective times, conflict gates and conservative account-specific blocked sizing | G03,T017 | Open; mitigation untested
RISK04 | Duplicate or missing account records | Critical | Possible | Yahoo mirrors or retry imports double capital | Underlying-account mapping, idempotency, source reconciliation, financial golden tests | G05,T014 | Open; mitigation untested
RISK05 | LLM hallucination or correlated review errors | High | Likely | Another agent endorses unsupported claim | Direct evidence checks, deterministic calculations, independent context, calibrated tests and abstention | G08,T039 | Open; mitigation untested
RISK06 | Backtest/LLM future information leakage | High | Likely | Many optimization trials overfit or know historical future | PIT snapshots, trial ledger, protected holdout, prospective shadow comparisons | G06,T033 | Open; mitigation untested
RISK07 | Optimizer alters its own approval rules | Critical | Possible | Higher score achieved by changing evaluator/tests | Protected assessor/keys, external promotion authority, sandbox denial tests | G10,T050 | Open; mitigation untested
RISK08 | Generated code escapes sandbox | Critical | Possible | Accesses host or production credentials | Qualified runtime, no socket/secrets, read-only mounts, egress controls and adversarial tests | G11,T062 | Open; mitigation untested
RISK09 | Budget/latency conflict | High | Likely | AI reviews expire or improvement never completes within USD20 | Atomic reservations, priority queues, one revision, representative resource feasibility proofs | G14,T061 | Open; mitigation untested
RISK10 | Options payoff mistaken for pathwise risk | Critical | Possible | Assignment leg exposure or unknown deliverable hidden | Contract/lifecycle model, collateral checks, unsupported status, case tests | G07,T035 | Open; mitigation untested
RISK11 | Cross-tenant data/model leakage | Critical | Possible | Caches/retrieval/job scope bypasses DB boundary | Composite isolation, RLS nonprivileged roles, per-tenant encryption/indices and adversarial tests | G11,T010 | Open; mitigation untested
RISK12 | Prompt injection and source tools abuse | Critical | Likely | Retrieved content orders secret release or trading | Untrusted evidence boundaries, typed tools, no broker writes, no candidate authority | G11,T062 | Open; mitigation untested
RISK13 | Provider authentication/terms changes | High | Likely | Previously supported route revoked or quota reduced | Versioned capability register, explicit degradation, permission requalification | G02,T002 | Open; mitigation untested
RISK14 | Scope-led launch exceeds commercial timing | High | Likely | All six improvement areas plus commercial gates take longer | Dependency waves, explicit gate dashboard, no silent scope reduction or artificial deadline | G16,T064 | Open; mitigation untested
RISK15 | Retention conflicts with reproducibility | High | Likely | Evidence deleted but old scorecard claims replay | Deletion state/tombstones, restricted benchmark claims, input availability flags | G12,T058 | Open; mitigation untested
RISK16 | Live/research/simulator logic drift | High | Possible | Different formulas yield misleading comparisons | Shared domain interfaces and versioned calculation conformance fixtures | G13,T018 | Open; mitigation untested
RISK17 | Currency/fees/corporate action accounting error | Critical | Possible | Economic performance and available cash misstated | Commodity-balanced decimal journal, fee convention, corporate-action test packs | G05,T012 | Open; mitigation untested
RISK18 | Subsequent strategy update overrides user choice | High | Possible | Maintainer release changes approved risk behavior | Separate release approval and user strategy adoption; pause unsupported old versions | G09,G10,T051 | Open; mitigation untested

## Decisions
APPROVED DECISION LINEAGE
Q1–Q69 reflect explicit decisions; Q70–Q79 are delegated design selections. No source conversation is replaced by unreviewed tracker edits.
Decision | Authority | Domain | Decision statement | Status | Requirement
Q1 | Explicit user decision | product | Personal-first with near-term multi-user commercialization; preserve tenant and deployment foundations from the start. | Accepted planning baseline | R001
Q2 | Explicit user decision | product | Primary purpose is portfolio-aware decisions plus frequent trading signals. | Accepted planning baseline | R002
Q3 | Explicit user decision | data | A useful no-paid-market-data baseline must not require paid AI; hosting and optional providers are separate. | Accepted planning baseline | R003
Q4 | Explicit user decision | data | Mandatory discovery is US-listed stocks and ETFs with currency-aware accounts. | Accepted planning baseline | R004
Q5 | Explicit user decision | security | First release proposes specific actions but never submits, modifies or cancels broker orders. | Accepted planning baseline | R005
Q6 | Explicit user decision | platform | Both hosted and complete self-hosted editions are release requirements. | Accepted planning baseline | R006
Q7 | Explicit user decision | compliance | Initial commercial audience includes Canadian and US residents. | Accepted planning baseline | R007
Q8 | Explicit user decision | strategies | Intraday swing discovery plus optional same-day opportunities; no sub-minute scalping requirement. | Accepted planning baseline | R008
Q9 | Explicit user decision | strategies | Frequent evaluation means timely qualifying changes, not a quota of trades. | Accepted planning baseline | R009
Q10 | Explicit user decision | risk | Separate investing and trading allocations with portfolio-wide limits. | Accepted planning baseline | R010
Q11 | Explicit user decision | data | Free mode may require a user-connected free provider account/key. | Accepted planning baseline | R011
Q12 | Explicit user decision | portfolio | Stale or unreconciled holdings/cash block affected portfolio-specific sizing. | Accepted planning baseline | R012
Q13 | Explicit user decision | platform | Independent open-source core and complete self-hosted application; no mandatory vendor-operated service. | Accepted planning baseline | R013
Q14 | Explicit user decision | data | Prioritized live monitoring plus broader scheduled discovery; tracked and streamed universes differ. | Accepted planning baseline | R014
Q15 | Explicit user decision | ai | Auditable rules and AI research both originate proposals; a separate agent evaluates actionable AI-mode proposals. | Accepted planning baseline | R015
Q16 | Explicit user decision | onboarding | MCQs and necessary numeric/date inputs propose a policy/strategy shortlist for explicit runtime approval. | Accepted planning baseline | R016
Q17 | Explicit user decision | options | Opt-in first-release options include long calls/puts, covered calls, cash-secured puts and defined-risk verticals. | Accepted planning baseline | R017
Q18 | Explicit user decision | ai | API and subscription access use provider-specific officially permitted routes and deployment qualification. | Accepted planning baseline | R018
Q19 | Explicit user decision | ai | Mandatory evidence/calculation verification is tiered; separate model review is required for AI-mode actions. | Accepted planning baseline | R019
Q20 | Explicit user decision | proposals | Action proposals expire and have invalidation conditions plus preserved version history. | Accepted planning baseline | R020
Q21 | Explicit user decision | compliance | Commercial legal and provider-rights clearance are release gates. | Accepted planning baseline | R021
Q22 | Explicit user decision | platform | Apache-2.0 is the selected application license, superseding AGPL proposals. | Accepted planning baseline | R022
Q23 | Explicit user decision | ai | Support audited rules-only and AI-enabled modes; evaluator covers both proposal origins in AI mode. | Accepted planning baseline | R023
Q24 | Explicit user decision | research | AI proposals qualify through evaluated research workflows and proposal-specific checks, not necessarily a backtested rule. | Accepted planning baseline | R024
Q25 | Explicit user decision | ai | Evaluator is a separate run/context; a different model family is optional and empirically justified. | Accepted planning baseline | R025
Q26 | Explicit user decision | ai | Material factual/evidence conflicts and hard risk failures block; forecast differences may be disclosed; revisions bounded. | Accepted planning baseline | R026
Q27 | Explicit user decision | ai | Frequent deterministic monitoring; AI on meaningful events/schedules/requests within budgets and deadlines. | Accepted planning baseline | R027
Q28 | Explicit user decision | improvement | All six improvement targets are in scope, including code and the optimizer itself. | Accepted planning baseline | R028
Q29 | Explicit user decision | improvement | Promotion uses predeclared scorecards with hard risk/privacy/evidence constraints, not recent returns alone. | Accepted planning baseline | R029
Q30 | Explicit user decision | improvement | Autonomous authorized experiments, human-controlled promotion of investment-affecting or code changes. | Accepted planning baseline | R030
Q31 | Explicit user decision | privacy | Private learning per user/installation by default; cross-user use requires separate consent and permitted data. | Accepted planning baseline | R031
Q32 | Explicit user decision | improvement | Separate experiment resource budgets; current monitoring and verification take priority. | Accepted planning baseline | R032
Q33 | Explicit user decision | improvement | All six improvement areas, code-level change and recursive optimizer change must work at first release. | Accepted planning baseline | R033
Q34 | Explicit user decision | governance | Material changes to enabled investment strategies require user adoption after release approval. | Accepted planning baseline | R034
Q35 | Explicit user decision | operations | Personal pilot incremental inference ceiling USD100/month; improvement maximum 20 percent (USD20). | Accepted planning baseline | R035
Q36 | Explicit user decision | platform | Single-machine container self-hosting without required Kubernetes/GPU/vendor service. | Accepted planning baseline | R036
Q37 | Explicit user decision | improvement | Demonstrate V0 optimizer proposing V1, independent evaluation, human promotion, then V1 running next cycle. | Accepted planning baseline | R037
Q38 | Explicit user decision | security | Generated code is isolated from production secrets, DB writes, unrestricted network and host control. | Accepted planning baseline | R038
Q39 | Explicit user decision | improvement | User learning is tenant-scoped; shared executable/optimizer changes are installation/release scoped. | Accepted planning baseline | R039
Q40 | Explicit user decision | research | Open evaluation framework and permitted starter corpus; distinguish synthetic/historical/prospective evidence. | Accepted planning baseline | R040
Q41 | Explicit user decision | product | Full scope and release gates take precedence over launch date; budget limits throughput rather than silently cutting scope. | Accepted planning baseline | R041
Q42 | Explicit user decision | portfolio | Partial portfolios allowed with scoped conclusions; outside-coverage assets retained with gaps. | Accepted planning baseline | R042
Q43 | Explicit user decision | portfolio | Multiple accounts/currencies with account-specific spendability and consolidated risk. | Accepted planning baseline | R043
Q44 | Explicit user decision | risk | Stock/ETF proposals cash-funded long-only, nonleveraged/noninverse; approved options remain. | Accepted planning baseline | R044
Q45 | Explicit user decision | evidence | Primary and permitted independent sources; optional social inputs clearly distinguished from facts. | Accepted planning baseline | R045
Q46 | Explicit user decision | portfolio | Tax-relevant records and warnings, not a comprehensive tax engine or automated tax-loss harvesting. | Accepted planning baseline | R046
Q47 | Explicit user decision | ux | Responsive web, in-app feed, configurable email/browser push; no native mobile/SMS launch requirement. | Accepted planning baseline | R047
Q48 | Explicit user decision | integrations | Small named set of tested read-only broker sync routes; CSV/manual fallback. | Accepted planning baseline | R048
Q49 | Explicit user decision | risk | Proposals form jointly feasible sets with explicit alternatives and internal capital commitments. | Accepted planning baseline | R049
Q50 | Explicit user decision | strategies | Initial actionable intraday proposals are regular-session only; research may run outside session. | Accepted planning baseline | R050
Q51 | Explicit user decision | privacy | Hosted/self-hosted migration is supported at first release. | Accepted planning baseline | R051
Q52 | Explicit user decision | privacy | Tamper-evident retained history, not indefinite private retention; explicit correction/deletion/backups. | Accepted planning baseline | R052
Q53 | Explicit user decision | integrations | CIBC import, Questrade/IBKR read-only sync, plus Wealthsimple sync and Yahoo CSV interoperability. | Accepted planning baseline | R053
Q54 | Explicit user decision | operations | Reference scale: 10 accounts, 250 instruments, 100000 records/user; hosted 100 users and 20 concurrent sessions. | Accepted planning baseline | R054
Q55 | Explicit user decision | product | Managed service pricing plus user-connected providers; independent self-hosted core and unbiased rankings. | Accepted planning baseline | R055
Q56 | Explicit user decision | ux | Dashboard-led portfolio/decision/research/governance workspaces; chat uses same verified state. | Accepted planning baseline | R056
Q57 | Explicit user decision | integrations | Yahoo tested CSV portfolio/watchlist import and compatible export; no auto-sync/data-adapter launch promise. | Accepted planning baseline | R057
Q58 | Explicit user decision | portfolio | Underlying accounts and data sources are separate; reconcile overlapping views without duplication. | Accepted planning baseline | R058
Q59 | Explicit user decision | strategies | All six versioned stock/ETF strategy families required; qualification status separate from catalogue inclusion. | Accepted planning baseline | R059
Q60 | Explicit user decision | risk | Conservative liquidity/spread/data/status-screened universe; optional speculative research cannot bypass gates. | Accepted planning baseline | R060
Q61 | Explicit user decision | strategies | Bounded versioned strategy configuration, not unrestricted hosted arbitrary-code or visual strategy builder. | Accepted planning baseline | R061
Q62 | Explicit user decision | strategies | Free baseline supports portfolio-specific rebalancing plus a qualified non-intraday long-only strategy. | Accepted planning baseline | R062
Q63 | Explicit user decision | simulation | User-facing application-managed virtual portfolios and optional approved-policy shadow tracking. | Accepted planning baseline | R063
Q64 | Explicit user decision | analytics | Versioned goal-appropriate/cash-flow-matched benchmarks and separate actual/simulated/recommendation scorecards. | Accepted planning baseline | R064
Q65 | Explicit user decision | research | Separate operational qualification, investment evidence and user eligibility; family-specific actionable-use gates. | Accepted planning baseline | R065
Q66 | Explicit user decision | data | Versioned feed specifications and qualified continuity/reinitialization for provider changes. | Accepted planning baseline | R066
Q67 | Explicit user decision | operations | Targets: 95 percent factual events within 5s of receipt; rules-only within 15s; AI intraday deadline at most 60s or earlier expiry. | Accepted planning baseline | R067
Q68 | Explicit user decision | risk | Explicit approved numerical account/allocation/concentration/planned-loss/scenario limits for sizing. | Accepted planning baseline | R068
Q69 | Explicit user decision | risk | Scoped loss/drawdown triggers pause new risk; monitoring and checked risk reduction continue; controlled resumption. | Accepted planning baseline | R069
Q70 | Delegated design selection | architecture | Typed Python core, TypeScript/React, PostgreSQL, analytical file/object storage and durable jobs; three authority paths. | Accepted planning baseline | R070
Q71 | Delegated design selection | portfolio | Reconciled decimal journal with explicit effective/publication/receipt/decision times; one calculation contract. | Accepted planning baseline | R071
Q72 | Delegated design selection | strategies | Interpretable six-family starting implementations; 6-month/200-day momentum and 15-minute ORB are unqualified research defaults. | Accepted planning baseline | R072
Q73 | Delegated design selection | integrations | Capability/rights/degraded-state registry; provider/entitlement changes require reassessment. | Accepted planning baseline | R073
Q74 | Delegated design selection | ai | Persisted bounded workflows, explicit model/runtime versions, no silent paid/provider fallback. | Accepted planning baseline | R074
Q75 | Delegated design selection | security | Read-only operation allowlists, secrets outside agents, tenant isolation including nonowner/nonbypass DB roles. | Accepted planning baseline | R075
Q76 | Delegated design selection | improvement | gVisor initial Linux sandbox qualification target; full recursive scope; reviewed signed promotion and compatible rollback. | Accepted planning baseline | R076
Q77 | Delegated design selection | operations | Hosted targets 99.9 percent availability, 15-minute RPO and 4-hour RTO; receipts not guarantees. | Accepted planning baseline | R077
Q78 | Delegated design selection | testing | End-to-end release journeys cover free mode, overlap, AI, intraday, options, risk pause, simulation, improvement, migration and isolation. | Accepted planning baseline | R078
Q79 | Delegated design selection | governance | Separate design choices from factual provider/legal/security/performance/economic gates. | Accepted planning baseline | R079

## Sources
DATED PRIMARY SOURCE REGISTER
Checked 8 October 2026. Current provider/legal facts must be requalified before release. Library excerpt references are not public URLs.
Source | Title | URL / library reference | Verification performed | Supported point | Limitation | Checked on
SRC-01 | Alpaca Market Data plans | https://docs.alpaca.markets/us/docs/about-market-data-api | Official documentation inspected | Individual Basic lists IEX-only stocks, 30 stock streams, 200 historical requests/minute, indicative options. Individual and business arrangements differ. | Provider/runtime/rights testing still required. | 2026-10-08
SRC-02 | Alpaca feed semantics | https://docs.alpaca.markets/us/docs/market-data-faq | Official documentation inspected | Historical feed selection is explicit; free SIP history requires end at least 15 minutes old. Subscription-default feed selection can change. | No assumption of consolidated live quotes in the free mode. | 2026-10-08
SRC-03 | Alpaca paper environment | https://docs.alpaca.markets/us/docs/paper-trading | Official documentation inspected | Paper simulation omits important real execution effects. Paper-only access is a candidate for free onboarding. | Our simulator must declare its own economics; paper results are not proof of real performance. | 2026-10-08
SRC-04 | SnapTrade broker access | https://docs.snaptrade.com/docs/broker-access-guide | Official documentation inspected | Broker guide lists supported integration routes, with production access requirements. | Test each broker, account type, auth method, deployment and field; names on a list are not acceptance evidence. | 2026-10-08
SRC-05 | SnapTrade trade detection | https://docs.snaptrade.com/docs/trade-detection | Official documentation inspected | Wealthsimple and Questrade trade detection is documented at five-minute-or-longer intervals. | Account-state freshness must be separate from quote and processing latency. | 2026-10-08
SRC-06 | Questrade API | https://www.questrade.com/api | Official documentation inspected | Personal users can access account/market information; API trade execution is limited to partner developers. | Read-only capabilities only; company integration permission is a separate gate. | 2026-10-08
SRC-07 | IBKR Web API | https://www.interactivebrokers.com/campus/ibkr-api-page/webapi-doc/ | Official documentation inspected | Read-only portfolio subset exists. Third-party vendor integration requires approval and a distinct authentication process. | No unattended commercial or local auth route assumed from a personal login. | 2026-10-08
SRC-08 | Wealthsimple activity export | https://help.wealthsimple.com/hc/en-ca/articles/39449252453019-View-your-account-activity-and-running-balance | Official documentation inspected | Activity CSV download is documented. | Real anonymized samples and corporate-action reconciliation are not yet tested. | 2026-10-08
SRC-09 | Yahoo portfolio CSV | https://help.yahoo.com/kb/finance-for-web/download-portfolio-data-yahoo-finance-sln15034.html | Official search excerpt only; direct open failed | Yahoo help describes portfolio/list CSV transfer. | Exact current columns, round-trip loss and transaction completeness remain sample-based qualification gates. Not a Yahoo market data license. | 2026-10-08
SRC-10 | SEC EDGAR APIs | https://www.sec.gov/search-filings/edgar-application-programming-interfaces | Official documentation inspected | SEC provides submissions and XBRL APIs. | Respect fair-access rules; publication dates, units and restatements require normalization. No analyst-consensus promise. | 2026-10-08
SRC-11 | Bank of Canada Valet | https://www.bankofcanada.ca/valet-api-how-to/ | Official documentation inspected | Valet has no usage charge, registration or access-key requirement; daily data can be cached. | Reference FX, not an executable conversion quote; respect terms and data timing. | 2026-10-08
SRC-12 | ChatGPT plan in other apps | https://help.openai.com/en/articles/20001542-using-your-chatgpt-plan-in-other-apps-and-sites | Official documentation inspected | Plan-funded requests are available in participating apps/tools subject to eligibility and plan rules. | App participation, deployment and permissible financial use must be qualified; no universal subscription API. | 2026-10-08
SRC-13 | Claude Code authentication rules | https://code.claude.com/docs/en/legal-and-compliance | Official documentation inspected | Native unmodified Claude Code authentication is distinguished from prohibited collection/intermediation of Claude.ai credentials by third parties. | Use API keys or approved native flow; no session-token proxy. Hosted feasibility remains open. | 2026-10-08
SRC-14 | xAI API authentication | https://docs.x.ai/developers/rest-api-reference/management/auth | Official documentation inspected | API keys authenticate inference requests as bearer credentials. | API adapter required; consumer-subscription access is not promised. | 2026-10-08
SRC-15 | PostgreSQL row security | https://www.postgresql.org/docs/current/ddl-rowsecurity.html | Official documentation inspected | Superusers, BYPASSRLS roles and ordinarily table owners can bypass row security. | Use nonowner/nonbypass service roles and explicit isolation tests; RLS alone is insufficient. | 2026-10-08
SRC-16 | gVisor overview | https://gvisor.dev/docs/ | Official documentation inspected | gVisor provides an application-kernel isolation approach integrated with container execution. | Chosen Linux sandbox qualification target, not proof of sufficient security or universal host compatibility. | 2026-10-08
SRC-17 | BCSC securities fundamentals | https://www.bcsc.bc.ca/industry/financial-technology-innovation/securities-law-fundamentals | Official documentation inspected | Being in the business of advising about securities can engage registration requirements, subject to applicable exemptions. | Counsel must classify this actual non-discretionary product per jurisdiction. A disclaimer is not clearance. | 2026-10-08
SRC-18 | SEC investor bulletin on robo-advisers | https://www.investor.gov/introduction-investing/general-resources/news-alerts/alerts-bulletins/investor-bulletins-45 | Official regulator guidance inspected | Automated investment advice has securities-law considerations, including SEC/state adviser frameworks. | Not a product-specific determination; map federal and relevant state obligations with counsel. | 2026-10-08
SRC-19 | FINRA stop-order risks | https://www.finra.org/investors/insights/stop-orders-factors-consider-during-volatile-markets | Official guidance inspected | A stop trigger does not guarantee the execution price, and stop-limit orders may not execute. | Planned stop loss is a scenario, not guaranteed maximum loss. | 2026-10-08
SRC-20 | OIC assignment | https://www.optionseducation.org/referencelibrary/faq/options-assignment | Official industry education inspected | American-style short options can be assigned before expiry. | Separate expiration payoff from pathwise collateral, assignment and settlement risk. | 2026-10-08
SRC-21 | OIC vertical put spreads | https://www.optionseducation.org/strategies/all-strategies/bear-put-spread | Official industry education inspected | Vertical-spread analysis includes early-assignment and financing consequences, not merely an expiry payoff. | Do not model a spread as an inseparable atomic position throughout its life. | 2026-10-08
SRC-22 | Probability of Backtest Overfitting | https://scholarworks.wmich.edu/math_pubs/42/ | Primary research landing page inspected | Bailey, Borwein, Lopez de Prado and Zhu discuss selection-related backtest overfitting and a diagnostic framework. | Diagnostics inform research; no universal test proves a trading edge. | 2026-10-08
SRC-23 | Apache License 2.0 | https://www.apache.org/licenses/LICENSE-2.0.txt | Official license text inspected | Chosen project license. Dependencies, datasets, prompts and model terms still require separate compatibility review. | Copyright ownership/contributor policy must be finalized before public publication. | 2026-10-08
SRC-24 | Codex AGENTS.md | https://learn.chatgpt.com/docs/agent-configuration/agents-md | Official documentation inspected | AGENTS.md provides repository instructions with discovery/precedence rules. | Verify actual client version and applicable instructions in the target repository. | 2026-10-08
SRC-25 | Codex execution plans | https://developers.openai.com/cookbook/articles/codex_exec_plans | Official documentation inspected | Persistent execution plans can specify goals, steps and verification evidence for longer work. | This bundle supplies its own bounded task contracts; no external plugin is required. | 2026-10-08
SRC-26 | Existing user AC/ECC compatibility guide | Library: Codex_AC_ECC_Setup.md, 2026-10-06 | User Library excerpt inspected | Existing guide uses AGENTS.md, CLAUDE.md and a shared .agentic state; configured checks must not be overwritten. | This bundle is an original project-specific handoff, not the ECC distribution or an installer. | 2026-10-08